## Slide 1
Move Azure Resources
aka
How we migrated 1.500 VMs over 3 subscriptions in one night.
Aka
You want to migrate Azure services ? Take a coffee and let PowerShell do the job for you.

## Slide 2
Many thanks to our sponsors:

## Slide 3
Fabien Dibot
Cloud Solution Architect @ Microsoft
Huge fan of cloud computing and automation
Former PowerShell MVP

## Slide 4: Context
2 months max to prepare and close the migration
CSP to EA migration
Classical Hub&Spoke based architecture
  One hub subscription
  3 Subscriptions
    Dev
    NonProd – 3 networks for zone segretation
    Prod – 3 Networks for zone segregation
No rollback possible, it’s all or nothing
All subscriptions are in the same tenant
Only 24h downtime accepted in CAB

## Slide 5: Assessment
Choose the correct method for migration
  Azure site recovery
  Azure Move API
Best way to assess 500+ resource groups ?
  API ?
  Manual validation using documentation ?
  Other ?
Plan actions based on outcomes
  Many Services not migrables
  Some services needs configuration/actions
Go/Nogo to open a change request
  Actions timing defined

## Slide 6: Demos

## Slide 7: Preparations
Recreate a new hub subscription
  Freeze all changes in production
  Backup & restore NVA config, UDR, NSG, etc
Create all new subscriptions and recreate RBAC custom roles
Alert applications owner of the migration schedule
Check & fix quotas on new subscriptions
Check PaaS services DNS name change and DNS records to update
Many POCs to validate strategy is OK and strong (ARM/Bicep to the rescue)

## Slide 8: 5 Steps
Take a snapshot of services/configuration
Backup RBAC
Move Services
Restore RBAC
Restore network connectivity
Test if all services have been transferred/restored correctly

## Slide 9: Demos
Backup RBAC
Snapshot services

## Slide 10: Demos
Merge

## Slide 11: How merge is working ?
Before merge: Backup & remove all non migrable resources
  It can take some time (ie: SQL Managed Instance)
Wave list containing resource groups with same network depency
  Loop on each resource group to migrate services inside
  Create a list of services
  Move them to a shared resource group containing VNet
End of merge : Remove Virtual Network peering
Duration: it depends (4/5min per RG)

## Slide 12: Demos
Transfert

## Slide 13: Next move
Immediately start recreating destroyed resources:
  SQL Managed Instances
  Application Gateways
Recreate network peering with hub Network

## Slide 14: Demos
Split

## Slide 15: How split works ?
Strong naming convention
  Aligned with RG Name
  Environment should be present in resource name
Move list of resources with app code per environment
… And then restore RBAC

## Slide 17: Lessons learned
Subscriptions in the same tenant
  Only solution to migrate CSP subscription to EA
Strong naming convention
Can’t move marketplace items
Not all services migrable, assessment mandatory
  Use API to test can take very long time (limited scope to one RG)
  Manual validation using documentation
    Some services need additional attention/reconfiguration
Go/Nogo based on outcomes
Plan not migrable services - backup/restore/recreate – ARM/Terraform/Bicep to the rescue
Virtual Network is key / You can’t share Virtual Network between subscriptions
You can move only one RG to the same target resource group
Many teams involved, so, a strong project management is needed
Involve Pro active Microsoft support … just in case it goes wrong 

## Slide 18: Resources
https://jacktracey.co.uk/migration/azure-subscription-migrations/
https://github.com/fabiendibot/ResourcesMove

## Slide 19
Q&A
15 minutes